## Engineering & Procurement
Form to GUID-8147259 | [15 empty] | Doc. No.: | FRM-8153664
[16 empty] | Version: | 1.0
Deliverable List for Engineering and Procurement
Sr No |  |  | List of Deliverables A = Approval AS = Deliverable to be As Built before Handover DR = Draft deliverable, Initial calculations, Sketches etc. D = Deliverable Prepared, Issued & Approved (where appropriate) R = Responsible S = Support U = Update Deliverable X= Required Service (Non- Deliverable or Support Function) | Novartis | Designer | Construction Manager | Commissioning Contractor | Qualification Contractor | Others | Initiation & Feasibility | Concept Design | Basic Design | Detailed Design | Construction & Installation | Startup (Commissioning & Qualification) | Handover
1 |  |  | PROJECT MANAGEMENT & CONTROLLING SERVICES
1 | 1 |  | General Services
1 | 1 | 1 | Project Management / Administration Services | A | R | - | - | - | - | S | X | X | X | X | X | -
1 | 1 | 2 | Project Controls Services | A | R | - | - | - | - | X | X | X | X | X | X | -
1 | 1 | 3 | Project Scope Statement (PSS) | R,A | S | S | S | S | S | - | D | U | U
1 | 1 | 4 | Project Managment Plan (PMP) | R,A | S | S | S | S | S | - | - | D | U | X | U | -
1 | 1 | 5 | Project Object Structure Plan | R,A | S | - | - | - | - | - | D | U | U |  |  | -
1 | 1 | 6 | Project Document Management & Archiving Plan | R,A | S | - | - | - | - | - | D | U | U | X | U | -
1 | 1 | 7 | Organization Charts | R,A | S | - | - | - | - | D | U | U | U | X | U | -
1 | 1 | 8 | Prepare & Maintain Staffing Plans (Planned, Forecast, Actuals) | R,A | S | - | - | - | - | D | U | U | U | X | U | -
1 | 1 | 9 | Overall Schedule & Detailed Schedule per Phase, per Discipline, with Basis of Schedule | A | R | S | S | S | S | D | U | U | U |  |  | -
1 | 1 | 10 | Cost Estimates, with Basis of Estimate | A | R | - | - | - | - | D | U | U | U | D | U | -
1 | 1 | 11 | Risk Registers | A | R | - | - | - | - | - | DR | D | U | X | U | -
1 | 1 | 12 | Change Management, and Registers | A | R | - | - | - | - | - | - | D | U |  |  | -
1 | 1 | 13 | Monthly Progress Reports | - | R | - | - | - | - | - | D | U | U | X,D | X | -
1 | 1 | 14 | Document Management Services | - | R | - | - | - | - | - | X | X | X | X | X | -
1 | 1 | 15 | Training Management, Co-ordination, documentation and Records | A | R | - | - | - | - | - | X,D | X,D | X,D | D | X,D | -
1 | 1 | 16 | Weekly Meetings, Co-ordination meetings - Including Minutes etc. | - | R | - | - | - | - | X,D | X,D | X,D | X,D | X | X | -
1 | 1 | 17 | Co-ordination with Design, Construction, Commissioning & Qualification Contractors | - | R | - | - | - | - | - | - | X | X | X | X | -
1 | 1 | 18 | Feasibility Report | A | R | - | - | - | - | D | - | - | - |  |  | -
1 | 1 | 19 | Concept Design Report | A | R | - | - | - | - | - | D | - | - |  |  | -
1 | 1 | 20 | Basic Design Report | A | R | - | - | - | - | - | - | D | - |  |  | -
1 | 2 |  | Investment Documentation
1 | 2 | 1 | Planning CAR | R,A | S | - | - | - | - | X | X | - | - |  |  | -
1 | 2 | 2 | Frame CAR | R,A | S | - | - | - | - | - | X | X | - |  |  | -
1 | 2 | 3 | Execution CAR | R,A | S | - | - | - | - | - | - | X | - |  |  | -
1 | 3 |  | Governance
1 | 3 | 1 | Design Reviews | R,A | S | - | - | - | - | - | X | X | X |  |  | -
1 | 3 | 2 | Value Improvement Reviews (VIR) | R,A | S | - | - | - | - | - | X | X | X |  |  | - | * Not Mandatory for Projects < 20MUSD
1 | 3 | 3 | Early Asset Management (EAM) | R,A | S | - | - | - | - | - | - | X | X | X | X | -
1 | 3 | 5 | Project Definition Rating Index (PDRI) | R,A | S | - | - | - | - | - | X | X | - |  |  | - | * Not Mandatory for Projects < 20MUSD
1 | 3 | 6 | Independent Reviews (Projects >200MUSD) | R,A | S | - | - | - | - | - | - | X | - |  |  | -
1 | 3 | 7 | Stage Gate Reviews | R,A | S | - | - | - | - | - | X | X | - |  |  | -
1 | 3 | 8 | Monthly Sponsor / Governance Meetings | R | S | - | - | - | - | - | X | X | X | X | X | -
1 | 4 |  | Comos/Sap
1 | 4 | 1 | COMOS Document Administration | R,A, | S | - | - | - | - | X | X | X | X | X | X | -
1 | 4 | 2 | COMOS Document Generation & Uploading | A | R | - | - | - | - | X,D | X,D | X,D | X,D | X,D | X,D | -
1 | 4 | 3 | SAP Data Entry & Uploading | R,A, | S | - | - | - | - | - | - | - | X,D | X | X,D | -
2 |  |  | PROCESS
2 | 1 |  | Process Description
2 | 1 | 1 | Basic Design Report | A | R | - | - | - | - | - | - | D | - |  |  | -
2 | 1 | 2 | Program Report | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 2 |  | Process-Block-Diagram (PBD)
2 | 2 | 1 | Process Block Diagram (PBD) | A | R | - | - | - | - | D | U | U | U |  |  | -
2 | 3 |  | Process-Flow-Diagram (PFD)
2 | 3 | 1 | Process Flow Diagram - System 1 | A | R | - | - | - | - | DR | D | U | U |  |  | -
2 | 3 | 2 | Process Flow Diagram - System 2 | A | R | - | - | - | - | DR | D | U | U |  |  | -
2 | 3 | 3 | Process Flow Diagram - System 3 | A | R | - | - | - | - | DR | D | U | U |  |  | -
2 | 4 |  | Operational Flow Diagram (OFD)
2 | 4 | 1 | Operational Flow Diagram - System 1 | A | R | - | - | - | - | - | D | U | U |  |  | -
2 | 4 | 2 | Operational Flow Diagram - System 2 | A | R | - | - | - | - | - | D | U | U |  |  | -
2 | 4 | 3 | Operational Flow Diagram - System 3 | A | R | - | - | - | - | - | D | U | U |  |  | -
2 | 5 |  | Media / Energy / Mass-balance
2 | 5 | 1 | Media / Utility Balance | A | R | - | - | - | - | DR | D | U | U |  |  | -
2 | 5 | 2 | Mass balance (Raw Material / Solvents etc.) | A | R | - | - | - | - | DR | D | U | U |  |  | -
2 | 5 | 3 | Mass balance (Media / Buffer) | A | R | - | - | - | - | DR | D | U | U |  |  | -
2 | 5 | 4 | Utility Consumption Matrix | A | R | - | - | - | - | DR | D | U | U |  |  | -
2 | 6 |  | Product / Raw material / Excipients data
2 | 6 | 1 | Product / Raw Material / Excipient Cata | R,A | S | - | - | - | - | - | D | U | U |  |  | -
2 | 6 | 2 | Quantities estimates | R,A | S | - | - | - | - | - | D | U | U |  |  | -
2 | 7 |  | Process Scheduling / Production Planning
2 | 7 | 1 | Process & Equipment Utilization Schedule | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 7 | 2 | Process Simulation Model | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 8 |  | Lists / Data
2 | 8 | 1 | P&ID List | - | R | - | - | - | - | - | DR | D | U |  |  | -
2 | 8 | 2 | Equipment List | A | R | - | - | - | - | DR | D | U | U |  |  | -
2 | 8 | 3 | Instrumentation List | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 8 | 4 | Process Data / Instrumentation Basis Data | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 8 | 5 | Fluid List (Process, Utilities, Wastes) | A | R | - | - | - | - | - | D | U | U |  |  | -
2 | 8 | 6 | Tie-in Schedule / List | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 8 | 7 | Manual Valve List | - | R | - | - | - | - | - | - | D | U |  |  | -
2 | 9 |  | Calculations
2 | 9 | 1 | General Process, Utility, Line sizing Calculations (Excludes Vendors Packages) | - | R | - | - | - | - | - | - | D | U |  |  | -
2 | 9 | 2 | Sizing Calculations for all Instruments, Control Valves etc. (Excludes Vendor Packages) | - | R | - | - | - | - | - | - | D | U |  |  | -
2 | 9 | 3 | Relief Device Sizing Calculations | - | R | - | - | - | - | - | - | D | U |  |  | -
2 | 9 | 4 | Pressure Loss Calculations (Excludes Vendor Packages) | - | R | - | - | - | - | - | - | - | D |  |  | -
2 | 10 |  | Process Safety
2 | 10 | 1 | Process Risk Assessments (Hazops) of Process, Utility and Waste Systems | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 10 | 2 | Hazop Chairman / Scribe | - | R | - | - | - | - | - | - | X | X |  |  | -
2 | 10 | 3 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
2 | 11 |  | Drawings - General
2 | 11 | 1 | Material, Personnel and Waste Flow Drawings | A | R | - | - | - | - | - | DR | D | U |  |  | -
2 | 11 | 2 | Containment Zoning Drawings | A | R | - | - | - | - | - | DR | D | U |  |  | -
2 | 11 | 3 | GMP Zoning Drawings | A | R | - | - | - | - | - | DR | D | U |  |  | -
2 | 11 | 4 | Hazardous Area Drawings | A | R | - | - | - | - | - | DR | D | U |  |  | -
2 | 12 |  | Interface Agreement
2 | 12 | 1 | Process interfaces for mobile equipment | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 12 | 2 | Process interfaces for non-mobile equipment | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 13 |  | User Requirement Specifications (URS) / Concepts / Strategies
2 | 13 | 1 | Solid, Liquid, Gaseous Waste Treatment Concept | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 13 | 2 | Basis of Safety (Process) | A | R | - | - | - | - | - | DR | D | U |  |  | -
2 | 13 | 3 | Zoning concept, Pressure levels and Cleanliness Concept | A | R | - | - | - | - | - | DR | D | U |  |  | -
2 | 13 | 4 | Material & Personnel Flow Concept | A | R | - | - | - | - | - | DR | D | U |  |  | -
2 | 13 | 5 | Containment Concept | A | R | - | - | - | - | - | DR | D | U |  |  | -
2 | 13 | 6 | Hazardous areas concept (Ex) | A | R | - | - | - | - | - | DR | D | U |  |  | -
2 | 13 | 8 | Interfaces (service tie in, power supply, energies, etc.) | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 13 | 9 | Cleaning Concept for Equipment and Facility | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 13 | 10 | CIP / SIP Equipment Cleaning Philosophy | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 13 | 11 | Single Use Strategy | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 14 |  | System User Requirements Specifications (Process)
2 | 14 | 1 | URS - System 1 | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 14 | 2 | URS - System 2 | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 14 | 3 | URS - System 3 | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 15 |  | System User Requirements Specifications (Clean Utilities)
2 | 15 | 1 | URS_Clean Steam Generation & Distribution | A | R | - | - | - | - | - | DR | D | U |  |  | -
2 | 15 | 2 | URS_Purified Water Generation & Distribution | A | R | - | - | - | - | - | DR | D | U |  |  | -
2 | 15 | 3 | URS_WFI Generation & Distribution | A | R | - | - | - | - | - | DR | D | U |  |  | -
2 | 15 | 4 | Process Gas URS (N2, O2, CO2, Air) | A | R | - | - | - | - | - | DR | D | U |  |  | -
2 | 15 | 5 | Functional Specifications per Functional Unit / Equipment | A | R | - | - | - | - | - | - | - | D |  |  | AS
2 | 16 |  | Equipment Requirement Standard (ERS) (Process)
2 | 16 | 1 | ERS - System 1 | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 16 | 2 | ERS - System 2 | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 16 | 3 | ERS - System 3 | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 17 |  | Process & Instrument Diagrams - (Process)
2 | 17 | 1 | Process P&ID - System 1 | A | R | - | - | - | - | - | - | D | U |  |  | AS
2 | 17 | 2 | Process P&ID - System 2 | A | R | - | - | - | - | - | - | D | U |  |  | AS
2 | 17 | 3 | Process P&ID - System 3 | A | R | - | - | - | - | - | - | D | U |  |  | AS
2 | 18 |  | Process & Instrument Diagrams - Clean Utility
2 | 18 | 1 | Clean Utility - System 1 | A | R | - | - | - | - | - | - | D | U |  |  | AS
2 | 18 | 2 | Clean Utility - System 2 | A | R | - | - | - | - | - | - | D | U |  |  | AS
2 | 18 | 3 | Clean Utility - System 3 | A | R | - | - | - | - | - | - | D | U |  |  | AS
2 | 19 |  | Process & Instrument Diagrams - Black Utility
2 | 19 | 1 | Black Utility - System 1 | A | R | - | - | - | - | - | - | D | U |  |  | AS
2 | 19 | 2 | Black Utility - System 2 | A | R | - | - | - | - | - | - | D | U |  |  | AS
2 | 19 | 3 | Black Utility - System 3 | A | R | - | - | - | - | - | - | D | U |  |  | AS
2 | 20 |  | Process & Instrument Diagrams - Waste Utilities
2 | 20 | 1 | Waste Utilities - System 1 | A | R | - | - | - | - | - | - | D | U |  |  | AS
2 | 20 | 2 | Waste Utilities - System 2 | A | R | - | - | - | - | - | - | D | U |  |  | AS
2 | 20 | 3 | Waste Utilities - System 3 | A | R | - | - | - | - | - | - | D | U |  |  | AS
2 | 21 |  | Process & Instrument Diagrams - Tie-ins
2 | 21 | 1 | Ties Ins - System 1 | A | R | - | - | - | - | - | - | D | U |  |  | AS
2 | 21 | 2 | Ties Ins - System 2 | A | R | - | - | - | - | - | - | D | U |  |  | AS
2 | 21 | 3 | Ties Ins - System 3 | A | R | - | - | - | - | - | - | D | U |  |  | AS
2 | 22 |  | Process & Instrument Diagrams - Demolition
2 | 22 | 1 | Demolition - System 1 | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 22 | 2 | Demolition - System 2 | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 22 | 3 | Demolition - System 3 | A | R | - | - | - | - | - | - | D | U |  |  | -
2 | 23 |  | Process Piping
2 | 23 | 1 | Review Piping Design | - | R | - | - | - | - | - | - | X | X | X |  | - | 3D Model (Overall model as well as individual 3D models for equipment packages)
2 | 24 |  | Process Construction Activities
2 | 24 | 1 | Approve Fabrication Drawings | - | R | - | - | - | - | - | - | - | X | X |  | -
3 |  |  | MECHANICAL
3 | 1 |  | User Requirement Specifications (URS) / Concepts / Strategies
3 | 1 | 1 | Maintenance / Asset Mangement Concept | A | R | - | - | - | - | - | - | D | U |  |  | -
3 | 2 |  | System User Requirements Specifications (Black Utilities / Waste)
3 | 2 | 1 | URS_Waste / Bio-waste Treatment System | A | R | - | - | - | - | - | - | D | U |  |  | -
3 | 2 | 2 | URS_Process Waste Neutralization System | A | R | - | - | - | - | - | - | D | U |  |  | -
3 | 2 | 1 | Functional Specifications per Functional Unit / Equipment | A | R | - | - | - | - | - | - | - | D |  |  | -
3 | 3 |  | Mechanical - General Requirements / Drawings / Lists
3 | 3 | 1 | Installation & Equipment drawings | A | R | - | - | - | - | - | - | - | D |  |  | -
3 | 3 | 2 | FEMECA Assessments (All Equipment) | A | R | - | - | - | - | - | - | - | D |  |  | -
3 | 3 | 3 | Material and welding specifications | A | R | - | - | - | - | - | - | - | D |  |  | -
3 | 3 | 4 | Quality Assurance Procedures | A | R | - | - | - | - | - | - | - | D |  |  | -
3 | 3 | 5 | General Specification for Mechanical Equipment | A | R | - | - | - | - | - | - | - | D |  |  | -
3 | 3 | 6 | Vendor Document Requirements | A | R | - | - | - | - | - | - | - | D |  |  | -
3 | 3 | 7 | Review Piping Design | A | R | - | - | - | - | - | - | X | X | X |  | - | 3D Model (Overall model as well as individual 3D models for equipment packages)
3 | 3 | 8 | Check Piping Calculations | A | R | - | - | - | - | - | - | X | X | X |  | -
3 | 3 | 9 | Pneumatic drawings | A | R | - | - | - | - | - | - | - | D |  |  | -
3 | 3 | 10 | Part list Pneumatic drawings | A | R | - | - | - | - | - | - | - | D |  |  | -
3 | 3 | 11 | Hydraulic drawings | A | R | - | - | - | - | - | - | - | D |  |  | -
3 | 3 | 12 | Part list Hydraulic drawings | A | R | - | - | - | - | - | - | - | D |  |  | -
3 | 3 | 13 | Equipment and System PED Calculations | A | R | - | - | - | - | - | - | - | D |  |  | -
3 | 3 | 14 | Spare part items List | A | R | - | - | - | - | - | - | - | D |  |  | -
3 | 3 | 15 | Bills of Materials | - | R | - | - | - | - | - | - | D | U |  |  | -
3 | 3 | 16 | Discipline Cost Estimates | A | R | - | - | - | - | - | D | U | U |  |  | -
3 | 3 | 17 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
3 | 4 |  | Equipment Data Sheets (Process, Utilities and Waste)
3 | 4 | 1 | Data sheet for Items / Equipment | A | R | - | - | - | - | - | - | D | U |  |  | -
3 | 4 | 2 | Data sheet for Vessels | A | R | - | - | - | - | - | - | D | U |  |  | -
3 | 5 |  | Equipment Package (RFQ / TBA / RFP) - Process Equipment
3 | 5 | 1 | Equipment Package 1 | A | R | - | - | - | - | - | - | D | U |  |  | -
3 | 5 | 2 | Equipment Package 2 | A | R | - | - | - | - | - | - | D | U |  |  | -
3 | 5 | 3 | Equipment Package 3 | A | R | - | - | - | - | - | - | D | U |  |  | -
3 | 5 | 21 | Equipment - Small Items | A | R | - | - | - | - | - | - | D | U |  |  | -
3 | 6 |  | Equipment (RFQ / TBA / RFP) - Utility & Process Waste Equipment
3 | 6 | 1 | Equipment Package 1 | A | R | - | - | - | - | - | - | D | U |  |  | -
3 | 6 | 2 | Equipment Package 2 | A | R | - | - | - | - | - | - | D | U |  |  | -
3 | 6 | 3 | Equipment Package 3 | A | R | - | - | - | - | - | - | D | U |  |  | -
3 | 7 |  | Mechanical Construction Activities
3 | 7 | 1 | Approve Fabrication Drawings | - | R | - | - | - | - | - | - | - | X | X |  | -
3 | 8 |  | Piping - Specification / Datasheets / Scope of Works
3 | 8 | 1 | General Piping Specifications | A | R | - | - | - | - | - |  | D | U |  |  | -
3 | 8 | 2 | 3D Execution Plan (Align with CSA, Building Services) | A | R | - | - | - | - | - | D | U | U |  |  | - | 3D Plan also detailed in Architectural
3 | 8 | 3 | Piping Material Take Off Philosophy | - | R | - | - | - | - | - | - | D | U |  |  | -
3 | 8 | 4 | Scope of Works / TBA - Mechanical Piping Package | A | R | - | - | - | - | - | - | - | D |  |  | -
3 | 9 |  | Piping - Lists, Schedules, Calculations, Reports
3 | 9 | 1 | Material Take Offs | - | R | - | - | - | - | - | DR | D | U |  |  | - | Takes offs required to support Estimates
3 | 9 | 2 | Line Lists | - | R | - | - | - | - | - | - | D | U |  |  | -
3 | 9 | 3 | Valve Lists | - | R | - | - | - | - | - | - | D | U |  |  | -
3 | 9 | 4 | Special Piping Items Lists | - | R | - | - | - | - | - | - | D | U |  |  | -
3 | 99 | 5 | 30, 60, 90, 100% Design Reviews, with Action Lists & Closeout | A | R | - | - | - | - | - | - | X | X |  |  | -
3 | 9 | 6 | Clash Management Reporting & Close out | - | R | - | - | - | - | - | - | X | X |  |  | -
3 | 9 | 7 | Bills of Materials | - | R | - | - | - | - | - | - | D | U |  |  | -
3 | 9 | 8 | Discipline Cost Estimates | A | R | - | - | - | - | - | D | U | U |  |  | -
3 | 9 | 9 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
3 | 10 |  | Piping - Drawings / Schematics / Layouts / Arrangements
3 | 10 | 1 | Mechanical Piping 3D Model | - | R | - | - | - | - | - | - | D | U |  |  | -
3 | 10 | 2 | 3D Model Administration and Space Management | - | R | - | - | - | - | - | - | X | X |  |  | -
3 | 10 | 3 | Isometrics Generation | - | R | - | - | - | - | - | - | - | D |  |  | -
3 | 10 | 4 | Equipment Arrangement Drawings (Per Area / Floor) | - | R | - | - | - | - | - | D | U | U |  |  | -
3 | 10 | 5 | Section Drawings (Per Area / Floor) | - | R | - | - | - | - | - | - | D | U |  |  | -
4 |  |  | CIVIL, STRUCTURAL, ARCHITECTURAL, FIRE & LIFT ENGINEERING
4 | 1 |  | Authority Applications / Closeout
4 | 1 | 1 | Planning Applications | R,A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 1 | 2 | Disability Access Applications | R,A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 1 | 3 | Fire Certificate Applications | R,A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 1 | 4 | Construction Permit | R,A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 1 | 5 | Review building permission regarding special requirements | S | R | - | - | - | - | - | - | - | X |  |  | -
4 | 1 | 7 | Organize inspections by Authorities at the end of the project | S | R | - | - | - | - | - | - | - | - | X |  | -
4 | 2 |  | Civil Engineering - Land / Procurement
4 | 2 | 1 | Land documentation | R,A | S | - | - | - | - |  | X | X | - |  |  | -
4 | 3 |  | Civil Engineering - Preparation work
4 | 3 | 1 | Site Survey / Geological reports | A | R | - | - | - | - | - | D | D | U |  |  | -
4 | 3 | 2 | Plans and documentation of existing underground services | R,A | S | - | - | - | - | - | - | D | U |  |  | -
4 | 3 | 3 | Provisional site & building boundaries / Site master plan Drawings | A | R | - | - | - | - | DR | D | U | U |  |  | -
4 | 3 | 4 | Connection Power / Utilities supply | A | R | - | - | - | - | DR | D | U | U |  |  | -
4 | 3 | 5 | Connection sewage-water industrial, foul water, rainwater | A | R | - | - | - | - | DR | D | U | U |  |  | -
4 | 3 | 6 | External Access / Roads | A | R | - | - | - | - | DR | D | U | U |  |  | -
4 | 4 |  | Civil Engineering - Specification / Calculations / Drawings
4 | 4 | 1 | User Requirements Specification for Civils | A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 4 | 2 | Civil Basis of Design / CSA Concept | A | R | - | - | - | - | - | D | U |  |  |  | -
4 | 4 | 3 | Earthworks Specifications | A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 4 | 4 | Drainage Specifications | A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 4 | 5 | Drainage Systems calculations | A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 4 | 6 | Roads, Paths & Paving's Specifications | A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 4 | 7 | Earthworks (General Bulk Excavation) General Arrangement Drawings | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 4 | 8 | Earthworks (General Bulk Excavation) Sections Drawings | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 4 | 9 | Ground floor under slab drainage Drawings | A | R | - | - | - | - | - | - | D | U |  |  | AS
4 | 4 | 10 | Ground floor under slab drainage Detail Drawings | A | R | - | - | - | - | - | - | - | D |  |  | AS
4 | 4 | 11 | Underground Sump / Utility Services Drawings | A | R | - | - | - | - | - | - | - | D |  |  | AS
4 | 4 | 12 | Site underground Storm Sewer Drawings | A | R | - | - | - | - | - | - | D | U |  |  | AS
4 | 4 | 13 | Site underground Sanitary Sewer Drawings | A | R | - | - | - | - | - | - | D | U |  |  | AS
4 | 4 | 14 | Site underground Process Sewer Drawings | A | R | - | - | - | - | - | - | D | U |  |  | AS
4 | 4 | 15 | Site underground Firemain Drawings | A | R | - | - | - | - | - | - | D | U |  |  | AS
4 | 4 | 16 | Site Underground Utilities Drawings | A | R | - | - | - | - | - | - | D | U |  |  | AS
4 | 4 | 17 | Site Roads / Paving's / Landscape Drawings | A | R | - | - | - | - | - | - | D | U |  |  | AS
4 | 4 | 18 | Bills of Materials | - | R | - | - | - | - | - | - | D | U |  |  | -
4 | 4 | 19 | Discipline Cost Estimates | A | R | - | - | - | - | - | D | U | U |  |  | -
4 | 4 | 20 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
4 | 5 |  | Structural Engineering - Specification / Calculations / Drawings
4 | 5 | 1 | General Structural Specifications | A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 5 | 2 | Structural Basis of Design / CSA Concept | A | R | - | - | - | - | - | D | U | - |  |  | -
4 | 5 | 3 | Load Take / Run down Calculations | - | R | - | - | - | - | - | - | D | U |  |  | -
4 | 5 | 4 | Foundation Calculations | - | R | - | - | - | - | - | - | D | U |  |  | -
4 | 5 | 5 | Structural calculation package | - | R | - | - | - | - | - | - | D | U |  |  | -
4 | 5 | 6 | Reinforcement Calculations | - | R | - | - | - | - | - | - | - | D |  |  | -
4 | 5 | 7 | Concrete Specification | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 5 | 8 | Steelwork Specification | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 5 | 9 | Structural Blockwork Specification | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 5 | 10 | Bills of Materials | - | R | - | - | - | - | - | - | D | U |  |  | -
4 | 5 | 11 | Discipline Cost Estimates | A | R | - | - | - | - | - | D | U | U |  |  | -
4 | 5 | 12 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
4 | 6 |  | Structural Engineering - Drawings
4 | 6 | 1 | Concrete Drawings and Sections (per Area / Level) | A | R | - | - | - | - | - | - | - | D |  |  | - | Drawing sets: (Formwork, Reinforcement, Steel-lists)
4 | 6 | 2 | Steelwork Drawings and Sections (per Area / Level) | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 6 | 3 | Cladding Steel Drawings per Elevation | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 6 | 4 | Lift / Stair Well Drawings | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 6 | 5 | Stair Flight / Landing Drawings | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 6 | 6 | External Piperack Drawings | A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 6 | 7 | Internal Piperack Drawings | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 6 | 8 | Platform Steel Drawings | A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 6 | 9 | Foundation Reinforcement Drawings | - | R | - | - | - | - | - | - | - | D |  |  | -
4 | 6 | 10 | Foundation Reinforcement Schedules | - | R | - | - | - | - | - | - | - | D |  |  | -
4 | 6 | 11 | Floor / Columns / Walls Reinforcement Drawings (per Area / Level) | - | R | - | - | - | - | - | - | - | D |  |  | -
4 | 6 | 12 | Floor / Columns / Walls Reinforcement Schedules (per Area / Level) | - | R | - | - | - | - | - | - | - | D |  |  | -
4 | 7 |  | Architectural Engineering - Specification / Datasheets / Drawings
4 | 7 | 1 | General Architectural Specifications | A | R | - | - | - | - | - | D | U | U |  |  | -
4 | 7 | 2 | Architectural Basis of Design | A | R | - | - | - | - | - | D | U | - |  |  | -
4 | 7 | 3 | Bills of Materials / Quantities for Scopes of Work Tenders | - | R | - | - | - | - | - | D | U | U |  |  | -
4 | 7 | 4 | 3D Model Design | A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 7 | 5 | Site Setting Out Plan | A | R | - | - | - | - | - | D | U | U |  |  | -
4 | 7 | 6 | Site Layout Plan Drawing | A | R | - | - | - | - | DR | D | U | U |  |  | -
4 | 7 | 7 | Site Facilities Drawing | A | R | - | - | - | - | DR | D | U | U |  |  | -
4 | 7 | 8 | Site Logistics Drawing | A | R | - | - | - | - | DR | D | U | U |  |  | -
4 | 7 | 9 | Building Layout Plan Drawings (per Area / Level) (1:200) | A | R | - | - | - | - | DR | D | U | U |  |  | AS
4 | 7 | 10 | Building Elevation Drawings (Per Area / Level) (1:100) | A | R | - | - | - | - | - | D | U | U |  |  | AS
4 | 7 | 11 | Building Sections (1:100) | A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 7 | 12 | Detailed Building Plans (per Area / Level) (1:50) | A | R | - | - | - | - | - | - | - | D |  |  | AS
4 | 7 | 13 | Sections of facades (horizontal and vertical) 1:50 | A | R | - | - | - | - | - | - | - | D |  |  | AS
4 | 7 | 14 | Ceiling Plans (per Area / Level) (1:50) | A | R | - | - | - | - | - | - | - | D |  |  | AS
4 | 7 | 15 | Room Data Sheets | A | R | - | - | - | - | - | D | U | U |  |  | -
4 | 7 | 16 | Stair Drawings | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 7 | 17 | Lift Drawings | A | R | - | - | - | - | - | - | - | D |  |  | - | Lift-Supplier must provide workshop drawings incl. Inlays in concrete
4 | 7 | 18 | Lockers/ Toilets/ Changing Plan, Typical sections & details | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 7 | 19 | Lab Layout Plan Drawings (1:100) | A | R | - | - | - | - | - | D | U | U |  |  | AS
4 | 7 | 20 | Lab Section Drawings (1:100) | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 7 | 21 | Lab Detail & Furniture Layout Drawings | A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 7 | 22 | Lab Elevation Drawings | A | R | - | - | - | - | - | - | - | D |  |  | AS
4 | 7 | 23 | Office Layout Plan Drawings (1:100) | A | R | - | - | - | - | - | - | D | U |  |  | AS
4 | 7 | 24 | Office Section Drawings (1:100) | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 7 | 25 | Office Room Furniture Layout Drawings | A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 7 | 26 | Office Elevation Drawings | A | R | - | - | - | - | - | - | - | D |  |  | AS
4 | 7 | 27 | Cleanroom Layout Plan Drawings (per Room / Area) | A | R | - | - | - | - | - | D | U | U |  |  | AS
4 | 7 | 28 | Cleanroom Ceiling Plan Drawings (per Room / Area) | A | R | - | - | - | - | - | - | - | D |  |  | AS
4 | 7 | 29 | Cleanroom Detail Drawings (per Room / Area) | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 7 | 30 | Cleanroom Wall Elevation Drawings /per Room / Area) | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 7 | 31 | Internal glazed screen elevations/ details (1:50) | A | R | - | - | - | - | - | - | - | D |  |  | AS
4 | 7 | 32 | Floor-plans mezzanine level 1:100 | A | R | - | - | - | - | - | - | D | U |  |  | AS
4 | 7 | 33 | Bills of Materials | - | R | - | - | - | - | - | - | D | U |  |  | -
4 | 7 | 34 | Discipline Cost Estimates | A | R | - | - | - | - | - | D | U | U |  |  | -
4 | 7 | 35 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
4 | 8 |  | Architectural Engineering - Finishes
4 | 8 | 1 | Standards for finishes, materials, colors (per Area / Level) | A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 8 | 2 | Finishes Schedules (per Area / Level)) | A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 8 | 3 | Door Elevations & Typical Detail Schedules (per Area / Level) | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 8 | 4 | Window, Ext door & Louvre schedules & Elevations (Per Area / Level) | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 8 | 5 | List of all doors incl. Functional detail description | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 9 |  | Fire Engineering
4 | 9 | 1 | Fire Suppression Performance Specification | A | R | - | - | - | - | - | - | D | U |  |  | -
4 | 9 | 2 | Fire protection / Emergency exits / Fire compartment Concept | A | R | - | - | - | - | - | DR | D | U |  |  | -
4 | 9 | 3 | Fire Suppression Schematic (Per Area / Level) | A | R | - | - | - | - | - | - | D | U |  |  | AS
4 | 9 | 4 | Fire Suppression Equipment Layout (per Area / Level) | A | - | - | - | - | R | - | - | D | U |  |  | AS
4 | 9 | 5 | Fire Suppression Sprinkler Routing Drawings (per Area / Level) | A | - | - | - | - | R | - | - | - | D |  |  | -
4 | 9 | 6 | Fire Suppression Layout Drawings (per Area / Level) | A | - | - | - | - | R | - | - | - | D |  |  | -
4 | 9 | 7 | Fire Suppression 3D Model Design | A | - | - | - | - | R | - | - | - | D |  |  | -
4 | 9 | 8 | Fire Suppression Commissioning Test Package | A | - | - | - | - | R | - | - | - | D | U |  | -
4 | 9 | 9 | Bills of Materials | - | R | - | - | - | - | - | - | D | U |  |  | -
4 | 9 | 10 | Discipline Cost Estimates | A | R | - | - | - | - | - | D | U | U |  |  | -
4 | 9 | 11 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
4 | 10 |  | Lift Engineering
4 | 10 | 1 | Lift Performance Specification | A | R | - | - | - | - | - | DR | D | U |  |  | -
4 | 10 | 2 | Lift Shaft Drawings | A | R | - | - | - | - | - | - | - | D |  |  | - | The specification drawings originate from the lift supplier but must be incorporated into the structural concrete plans by the architect/engineer
4 | 10 | 3 | Lift Arrangement Drawings | A | - | - | - | - | R | - | - | - | D |  |  | -
4 | 10 | 4 | Lift Miscellaneous Detail Drawings | A | - | - | - | - | R | - | - | - | D |  |  | -
4 | 10 | 5 | Lifts Commissioning & Test Package | A | - | - | - | - | R | - | - | - | D |  |  | -
4 | 10 | 6 | Bills of Materials | - | R | - | - | - | - | - | - | D | U |  |  | -
4 | 10 | 7 | Discipline Cost Estimates | A | R | - | - | - | - | - | D | U | U |  |  | -
4 | 10 | 8 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
4 | 11 |  | CSA - Scopes of Work
4 | 11 | 1 | Scope of Works / TBA - Site Enabling Works | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 11 | 2 | Scope of Works / TBA - External Works, Roads, Landscaping etc. | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 11 | 3 | Scope of Works / TBA - Excavations | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 11 | 4 | Scope of Works / TBA - Foundations and Building Shell & Core | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 11 | 5 | Scope of Works / TBA - Structural Steel | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 11 | 6 | Scope of Works / TBA - Structural Concrete Including Foundations | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 11 | 7 | Scope of Works / TBA - Building Enclosure | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 11 | 8 | Scope of Works / TBA - Roof Finishes | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 11 | 9 | Scope of Works / TBA - Internal Fit out & Finishes | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 11 | 10 | Scope of Works / TBA - Flooring | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 11 | 11 | Scope of Works / TBA - Cleanrooms | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 11 | 12 | Scope of Works / TBA - Cold / Warm Rooms | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 11 | 13 | Scope of Works / TBA - Fire Protection | A | R | - | - | - | - | - | - | - | D |  |  | -
4 | 11 | 14 | Scope of Works / TBA - Lifts | A | R | - | - | - | - | - | - | - | D |  |  | -
5 |  |  | ELECTRICAL
5 | 1 |  | User Requirement Specifications (URS) / Concepts
5 | 1 | 1 | User Requirement Specification (URS) for Electrical Systems | A | R | - | - | - | - | - | - | D | U |  |  | -
5 | 1 | 2 | Functional Specifications Electrical | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 1 | 3 | Earthing Concept | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 1 | 4 | Lightning Design Concept | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 1 | 5 | Emergency Power / UPS Concept | A | R | - | - | - | - | - | DR | D | U |  |  | -
5 | 1 | 6 | Fire Detection Concept | A | R | - | - | - | - | - | DR | D | U |  |  | -
5 | 2 |  | Specification / Datasheets / Scope of Works
5 | 2 | 1 | General Electrical Specifications (Panels, Cabling etc.) | A | R | - | - | - | - | - | - | D | U |  |  | -
5 | 2 | 2 | Motor specifications | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 2 | 3 | Specification / Datasheet / MR / TBA - MCC | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 2 | 4 | Specification / Datasheet / MA / TBA- VFD/VSD | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 2 | 5 | Specification / Datasheet / MR / TBA- Transformers | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 2 | 6 | Specification / Datasheet / MR / TBA - MV Switchgear | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 2 | 7 | Specification / Datasheet / MR / TBA - LV Switchgear | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 2 | 8 | Specification / Datasheet / TBA - UPS | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 2 | 9 | Specification / Datasheet / MR / TBA - General Services Panels | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 2 | 10 | Scope of Works / TBA - E&I Main Package | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 2 | 11 | Scope of Works / TBA -Temporary Electrics | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 2 | 12 | Scope of Works / TBA - Fire and Gas Detection | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 2 | 13 | Scope of Works / TBA - CCTV and Security Systems | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 2 | 14 | Scope of Works / TBA - Door Access Systems | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 3 |  | Lists, Schedules, Calks, Reports
5 | 3 | 1 | Electrical Parameter lists | - | R | - | - | - | - | - | - | D | U |  |  | AS
5 | 3 | 2 | Motors and Consumer lists | - | R | - | - | - | - | - | DR | D | U |  |  | AS
5 | 3 | 3 | Electrical load list | - | R | - | - | - | - | - | - | D | U |  |  | AS
5 | 3 | 4 | Cable Schedule | - | R | - | - | - | - | - | - | DR | D |  |  | AS
5 | 3 | 5 | Luminaire Schedule | - | R | - | - | - | - | - | - | DR | D |  |  | AS
5 | 3 | 6 | Network Patching Schedules | - | R | - | - | - | - | - | - | - | D |  |  | AS
5 | 3 | 7 | Distribution Board Schedule | - | R | - | - | - | - | - | - | - | D |  |  | AS
5 | 3 | 8 | Termination Schedule | - | R | - | - | - | - | - | - | - | D |  |  | AS
5 | 3 | 9 | Schedule of Breaker Settings | - | R | - | - | - | - | - | - | - | D |  |  | AS
5 | 3 | 10 | ATEX Report | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 3 | 11 | Hazardous Area Classification Report | A | R | - | - | - | - | - | - | D | U |  |  | -
5 | 3 | 12 | Electrical/Cable Calculations | - | R | - | - | - | - | - | - | - | D |  |  | -
5 | 3 | 13 | Temporary Electrics Schedules, lists etc. | - | R | - | - | - | - | - | - | - | D |  |  | -
5 | 3 | 14 | Bills of Materials | - | R | - | - | - | - | - | - | D | U |  |  | -
5 | 3 | 15 | Discipline Cost Estimates | A | R | - | - | - | - | - | D | U | U |  |  | -
5 | 3 | 16 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
5 | 4 |  | Drawings / Schematics / Layouts / Arrangements
5 | 4 | 1 | Low and Medium Voltage Single Line Diagrams | A | R | - | - | - | - | - | DR | D | U |  |  | AS
5 | 4 | 2 | MCC Single line Diagrams | A | R | - | - | - | - | - | DR | D | U |  |  | AS
5 | 4 | 3 | Electrical Rooms Layouts and Sections | A | R | - | - | - | - | - | - | D | U |  |  | -
5 | 4 | 4 | Electrical cabinet layout and arrangements | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 4 | 5 | Electrical drawings (incl. power distribution) | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 4 | 6 | 3D Model Design, including ladders, Trays etc. | A | R | - | - | - | - | - | - | D | U |  |  | -
5 | 4 | 7 | Installation drawings (incl. cable ladder, trays layout) | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 4 | 8 | Cable Containment Layouts (Internal / External) | A | R | - | - | - | - | - | - | - | D |  |  | -
5 | 4 | 9 | General Services and Motive Power drawings | A | R | - | - | - | - | - | - | D | U |  |  | -
5 | 4 | 10 | Normal and Emergency Lighting Schematics | A | R | - | - | - | - | - | - | D | U |  |  | -
5 | 4 | 11 | Lighting Layout Drawings | A | R | - | - | - | - | - | - | D | U |  |  | AS
5 | 4 | 12 | Fire Alarm Drawings | A | R | - | - | - | - | - | - | D | D |  |  | AS
5 | 4 | 13 | Security and Communication drawings | A | R | - | - | - | - | - | - | - | D |  |  | AS
5 | 4 | 14 | Building Earthing System Schematic diagrams | A | R | - | - | - | - | - | - | DR | D |  |  | AS
5 | 4 | 15 | Lightning Protection System Layout | A | R | - | - | - | - | - | - | DR | D |  |  | AS
5 | 4 | 16 | Communication and Data Network Drawings | A | R | - | - | - | - | - | - | - | D |  |  | AS
5 | 4 | 17 | Temporary Electrics (Construction) Drawings | A | R | - | - | - | - | - | - | - | D |  |  | -
6 |  |  | INSTRUMENTATION
6 | 1 |  | User Requirement Specifications (URS) / Concepts
6 | 1 | 1 | User Requirement Specification (URS) for Instrumentation | A | R | - | - | - | - | - | - | D | U |  |  | -
6 | 1 | 2 | General Instrumentation Specifications | A | R | - | - | - | - | - | - | D | U |  |  | -
6 | 2 |  | Specification / Datasheets / Scope of Works
6 | 2 | 1 | Specification / Datasheet / MR / TBA - Remote I/O Panels | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 2 | Specification / Datasheet / MA / TBA- ON / OFF Valves | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 3 | Specification / Datasheet / MR / TBA- Control Valves | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 4 | Specification / Datasheet / MR / TBA - Safety / Relief Valves | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 5 | Specification / Datasheet / MR / TBA - Safety Rupture Discs | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 6 | Specification / Datasheet / MR / TBA - Diaphragm Valves | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 7 | Specification / Datasheet / TBA - Sanitary Control Valves | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 8 | Specification / Datasheet / TBA - Pressure Regulators | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 9 | Specification / Datasheet / TBA - Sanitary Pressure Regulators | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 10 | Specification / Datasheet / MR / TBA - Pressure Transmitters | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 11 | Specification / Datasheet / MR / TBA - Pressure Switches | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 12 | Specification / Datasheet / MR / TBA - Pressure Gauges | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 13 | Specification / Datasheet / MR / TBA - Flowmeters | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 14 | Specification / Datasheet / MR / TBA - Flow Switches | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 15 | Specification / Datasheet / MR / TBA - Flow Gauges | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 16 | Specification / Datasheet / MR / TBA - Temperature Transmitters | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 17 | Specification / Datasheet / MR / TBA - Temperature Switches | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 18 | Specification / Datasheet / MR / TBA - Temperature Indicators or Wells | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 19 | Specification / Datasheet / MR / TBA - Level Transmitters | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 20 | Specification / Datasheet / MR / TBA - Level Gauges | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 21 | Specification / Datasheet / MR / TBA - Level Switches | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 22 | Specification / Datasheet / MR / TBA - Weight Cells | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 23 | Specification / Datasheet / MR / TBA - pH Transmitters | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 24 | Specification / Datasheet / MR / TBA - Analyzers | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 25 | Specification / Datasheet / MR / TBA - Conductivity Transmitters | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 2 | 26 | Scope of Works / TBA - E & I Main Package | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 3 |  | Lists, Schedules, Calculations, Reports
6 | 3 | 1 | Instrument Index - Process, Utilities and Building Services | A | R | - | - | - | - | - | - | D | U |  |  | -
6 | 3 | 2 | Instrument I/O List - Process, Utilities and Building Services | A | R | - | - | - | - | - | - | D | U |  |  | -
6 | 3 | 3 | Instrument classification (Safety,GxP,etc) | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 3 | 4 | Instrument Alarm Lists | A | R | - | - | - | - | - | - | - | D |  |  | AS
6 | 3 | 5 | Instrument Parameter Lists | A | R | - | - | - | - | - | - | - | D |  |  | AS
6 | 3 | 6 | Instrument Cable Schedule | - | R | - | - | - | - | - | - | - | D |  |  | -
6 | 3 | 7 | Instrument Tube Schedule | - | R | - | - | - | - | - | - | - | D |  |  | -
6 | 3 | 8 | Instrument Panel Schedule | - | R | - | - | - | - | - | - | - | D |  |  | -
6 | 3 | 9 | Instrument Termination Schedule | - | R | - | - | - | - | - | - | - | D |  |  | AS
6 | 3 | 10 | Bus Segment Calculations | - | R | - | - | - | - | - | - | - | D |  |  | AS
6 | 3 | 11 | Calculation / Instrument Sizing | - | R | - | - | - | - | - | - | - | D |  |  | -
6 | 3 | 12 | Sensor Need / Risk Assessment | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 3 | 13 | SIL Assessment / Calculations | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 3 | 14 | Vendor Certificates (ATEX, Calibration) | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 3 | 15 | Bill of Material : Instruments | - | R | - | - | - | - | - | - | D | U |  |  | -
6 | 3 | 16 | Bill of Material : Valves and fittings | - | R | - | - | - | - | - | - | D | U |  |  | -
6 | 3 | 17 | Discipline Cost Estimates | A | R | - | - | - | - | - | D | U | U |  |  | -
6 | 3 | 18 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
6 | 4 |  | Drawings / Schematics / Layouts / Arrangements
6 | 4 | 1 | Installation Guideline Instruments / Hook-Ups | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 4 | 2 | Cable Block Diagrams | - | R | - | - | - | - | - | - | - | D |  |  | AS
6 | 4 | 3 | Instrument Loop Drawings | - | R | - | - | - | - | - | - | - | D |  |  | AS
6 | 4 | 4 | Control Room Layout Drawings | A | R | - | - | - | - | - | - | D | U |  |  | AS
6 | 4 | 5 | Instrument Panel Location Drawings | A | R | - | - | - | - | - | - | D | U |  |  | AS
6 | 4 | 6 | Bus segment block wiring diagrams for Instruments | A | R | - | - | - | - | - | - | - | D |  |  | -
6 | 4 | 7 | Bus segment block wiring diagrams for Motors | A | R | - | - | - | - | - | - | - | D |  |  | -
7 |  |  | PROCESS CONTROL / AUTOMATION
7 | 1 |  | Distributed Control System (PAS & RMS) - Software Design
7 | 1 | 2 | ERES Assessment | R,A | - | - | - | - | - | - | - | D | U |  |  | -
7 | 1 | 3 | User Requirement Specifications Systems | R,A | - | - | - | - | - | - | - | DR | D |  |  | -
7 | 1 | 5 | Equipment Requirement Specifications Systems | R,A | - | - | - | - | - | - | DR | D | U |  |  | -
7 | 1 | 6 | Graphics Specifications | R,A | - | - | - | - | - | - | - | D | U |  |  | -
7 | 1 | 7 | Alarm Specifications | R,A | - | - | - | - | - | - | - | D | U | U | U | AS
7 | 1 | 8 | Functional Specifications Process | R,A | R | - | - | - | - | - | - | - | D | U | U | AS
7 | 1 | 9 | Functional Specifications Clean Utilities | A | R | - | - | - | - | - | - | - | D | U | U | AS
7 | 1 | 10 | Functional Specifications Black Utilities | A | R | - | - | - | - | - | - | - | D | U | U | AS
7 | 1 | 11 | Functional Specifications Room Monitoring | R,A | - | - | - | - | - | - | - | - | D | U | U | AS
7 | 1 | 12 | Functional Specifications Interfaces | R,A | R | - | - | - | - | - | - | - | D | U | U | AS
7 | 1 | 13 | Software Design Specifications Process | - | R | - | - | - | R | - | - | - | D | U | U | AS
7 | 1 | 14 | Software Design Specifications Clean Utilities | - | - | - | - | - | R | - | - | - | D | U | U | AS
7 | 1 | 15 | Software Design Specifications Black Utilities | - | - | - | - | - | R | - | - | - | D | U | U | AS
7 | 1 | 16 | Software Design Specifications Room Monitoring | - | - | - | - | - | R | - | - | - | D | U | U | AS
7 | 1 | 17 | Data Map/Bit Map | - | R | - | - | - | - | - | - | - | D |  |  | AS
7 | 1 | 18 | Generation of Software Test Plan | R,A | R | - | - | - | - | - | - | - | D |  |  | -
7 | 1 | 19 | Generation of Software Test Specifications | R,A | R | - | - | - | - | - | - | - | D |  |  | -
7 | 1 | 20 | Software Procurement (Licenses etc.) | R,A | - | - | - | - | - | - | - | - | X |  |  | -
7 | 1 | 21 | Software Typicals | - | - | - | - | - | R | - | - | - | D |  |  | -
7 | 1 | 22 | Development of Software | - | - | - | - | - | R | - | - | - | X |  |  | -
7 | 1 | 23 | Develop Software Modules Classes | - | - | - | - | - | R | - | - | D | U |  |  | -
7 | 1 | 24 | Instantiation of Software Classes | - | - | - | - | - | R | - | - | D | U |  |  | -
7 | 1 | 25 | Software Design Review | R,A | R | - | - | - | - | - | - | - | X |  |  | -
7 | 1 | 26 | Software Code Review | R,A | R | - | - | - | - | - | - | - | X |  |  | -
7 | 2 |  | Distributed Control System (PAS & RMS) - Hardware Design
7 | 2 | 1 | DCS Network Infrastructure Design (Architecture) | A | R | - | - | - | R | - | DR | D | U | U | U | AS
7 | 2 | 2 | Hardware Typicals | - | - | - | - | - | R | - | - |  | D |  |  | -
7 | 2 | 4 | Hardware Design Specifications | - | - | - | - | - | R | - | - | D | U | U | U | AS
7 | 2 | 5 | Hardware Supply | - | - | - | - | - | R | - | - | - | X |  |  | -
7 | 2 | 6 | Bills of Materials | - | R | - | - | - | - | - | - | D | U |  |  | -
7 | 2 | 7 | Discipline Cost Estimates (Hardware & Software) | A | R | - | - | - | - | - | D | U | U |  |  | -
7 | 2 | 8 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
7 | 3 |  | IT Network Architecture (C-Layer / Modbus TCP)
7 | 3 | 1 | User Requirement Specifications IT | R,A | - | - | - | - | - | - | - | D | U | U | U | AS
7 | 3 | 2 | Functional Design Specifications | A | - | - | - | - | R | - | - | - | D | U | U | AS
7 | 3 | 3 | Overall Network Architecture Drawing | A | - | - | - | - | R | - | - | D | U | U | U | AS
7 | 4 |  | Manufacturing Execution System (MES)
7 | 4 | 1 | ERES Assessment | R,A | - | - | - | - | - | - | - | D | U |  |  | -
7 | 4 | 2 | User Requirement Specifications | R,A | - | - | - | - | - | - | - | D | U | U | U | AS
7 | 4 | 3 | Business Process Mapping | R,A | - | - | - | - | - | - | - | - | D
7 | 4 | 4 | Functional Design Specifications | A | - | - | - | - | R | - | - | - | D | U | U | AS
7 | 4 | 5 | Hardware Design Specifications | - | - | - | - | - | R | - | - | D | U | U | U | AS
7 | 4 | 6 | Software Modules Development | - | - | - | - | - | R | - | - | - | D |  |  | -
7 | 4 | 7 | Creation of Masters (i.e. Material Masters, MBRs, EBRs) | - | - | - | - | - | R | - | - | - | D | U | U | AS
7 | 4 | 8 | Software Design Review | R,A | - | - | - | - | - | - | - | - | X |  |  | -
7 | 4 | 9 | Software Code Review | R,A | - | - | - | - | - | - | - | - | X |  |  | -
7 | 4 | 10 | Bills of Materials | - | R | - | - | - | - | - | - | D | U |  |  | -
7 | 4 | 11 | Discipline Cost Estimates | A | R | - | - | - | - | - | D | U | U |  |  | -
7 | 4 | 12 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
7 | 5 |  | Historian System
7 | 5 | 1 | ERES Assessment | R,A | - | - | - | - | - | - | - | D | U |  |  | -
7 | 5 | 2 | User Requirement Specifications | R,A | - | - | - | - | - | - | - | D | U | U | U | AS
7 | 5 | 3 | Tag List | R,A | - | - | - | - | - | - | - | - | D | U |  | -
7 | 5 | 4 | Functional Design Specifications | A | - | - | - | - | R | - | - | - | D | U | U | AS
7 | 5 | 5 | Hardware Design Specifications | A | - | - | - | - | R | - | - | - | D | U | U | AS
7 | 5 | 6 | Software Modules | - | - | - | - | - | R | - | - | - | D |  |  | -
7 | 5 | 7 | Software Design Review | R,A | - | - | - | - | - | - | - | - | X |  |  | -
7 | 5 | 8 | Software Code Review | R,A | - | - | - | - | - | - | - | - | X |  |  | -
7 | 5 | 9 | Bills of Materials | - | R | - | - | - | - | - | - | D | U |  |  | -
7 | 5 | 10 | Discipline Cost Estimates | A | R | - | - | - | - | - | D | U | U |  |  | -
7 | 5 | 11 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
8 |  |  | BUILDING SERVICES
8 | 1 |  | User Requirement Specifications (URS) / Concepts
8 | 1 | 1 | User Requirement Specification (URS) for Systems | R,A | - | - | - | - | - | - | - | D | U |  |  | -
8 | 1 | 2 | Functional Description for HVAC | A | R | - | - | - | - | - | - | D | U |  |  | AS
8 | 2 |  | Specification / Datasheets / Scope of Works
8 | 2 | 1 | General Building Services Specifications | A | R | - | - | - | - | - | - | D | U |  |  | -
8 | 2 | 2 | Technical Design Specification / Datasheet / MR / TBA - AHUs | A | R | - | - | - | - | - | - | - | D |  |  | -
8 | 2 | 3 | Technical Design Specification / Datasheet / MA / TBA- Extract Fans | A | R | - | - | - | - | - | - | - | D |  |  | -
8 | 2 | 4 | Technical Design Specification / Datasheet / MR / TBA- HEPA Filter Boxes | A | R | - | - | - | - | - | - | - | D |  |  | -
8 | 2 | 5 | Technical Design Specification / Datasheet / MR / TBA - VAV / CAV Valves | A | R | - | - | - | - | - | - | - | D |  |  | -
8 | 2 | 6 | Technical Design Specification / Datasheet / MR / TBA - AC Units | A | R | - | - | - | - | - | - | - | D |  |  | -
8 | 2 | 7 | Technical Design Specification / Datasheet / MR / TBA - Instrumentation | A | R | - | - | - | - | - | - | - | D |  |  | -
8 | 2 | 8 | Scope of Works / TBA - HVAC Package | A | R | - | - | - | - | - | - | - | D |  |  | -
8 | 2 | 9 | Scope of Works / TBA -HVAC Testing & Balancing | A | R | - | - | - | - | - | - | - | D |  |  | -
8 | 2 | 10 | Scope of Works / TBA - BMS Package | A | R | - | - | - | - | - | - | - | D |  |  | -
8 | 2 | 11 |  | A | R | - | - | - | - | - | - | - | D |  |  | -
8 | 3 |  | BMS Requirements
8 | 3 | 1 | Management Level (SCADA)
8 | 3 | 2 | ERS BMS | R,A | - | - | - | - | - | - | - | D | U |  |  | -
8 | 3 | 3 | User Requirement Specification (URS) for Systems | R,A |  | - | - | - | - | - | - | D | U |  |  | -
8 | 3 | 4 | BMS Network Architecture Diagram (physical & logical) | A | R | - | - | - | - | - | - | D | U |  |  | AS
8 | 3 | 5 | Functional Specification | A | R | - | - | - | - | - | - | - | D |  |  | AS
8 | 3 | 6 | Software Design Specification | A | - | - | - | - | R | - | - | - | D |  |  | -
8 | 3 | 7 | Hardware Design Specification | A | R | - | - | - | - | - | - | - | D |  |  | -
8 | 3 | 8 | Operating manual | A | - | - | - | - | R | - | - | - | - | D |  | -
8 | 3 | 9 | FMECA (leads to Maintenance Plan & Spare Part needs) | R,A | S | - | - | - | S | - | - | - | D |  |  | -
8 | 3 | 2 | Automation for Control Level | - | - | - | - | - | - | - | - | - | - |  |  | -
8 | 3 | 1 | Functional Specification | A | S | - | - | - | R | - | - | - | D |  |  | AS
8 | 3 | 2 | Configuration Specification | A | S | - | - | - | R | - | - | - | D |  |  | AS
8 | 3 | 3 | HVAC IO list | A | S | - | - | - | R | - | - | D | U |  |  | AS
8 | 3 | 4 | HVAC Alarm list | A | S | - | - | - | R | - | - | DR | D |  |  | AS | On projects executed in COMOS list can be generated from the tool
8 | 3 | 5 | HVAC Sensor & Instrument List | A | S | - | - | - | R | - | - | D | U |  |  | AS | On projects executed in COMOS list can be generated from the tool
8 | 3 | 6 | HVAC Parameter list | A | S | - | - | - | R | - | - | - | D |  |  | AS
8 | 3 | 7 | Loop drawings HVAC | A | R | - | - | - | - | - | - | - | D |  |  | AS
8 | 3 | 8 | Pneumatic Drawings | A | R | - | - | - | - | - | - | - | D |  |  | AS
8 | 3 | 9 | FMECA (leads to Maintenance Plan & Spare Part needs) | R,A | - | - | - | - | S | - | - | - | D |  |  | -
8 | 3 | 10 | Bills of Materials | - | R | - | - | - | - | - | - | D | U |  |  | -
8 | 3 | 11 | Discipline Cost Estimates | A | R | - | - | - | - | - | D | U | U |  |  | -
8 | 3 | 12 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
8 | 4 |  | RMS Requirements
8 | 4 | 1 | ERS RMS | R,A | - | - | - | - | - | - | - | D | U |  |  | -
8 | 4 | 2 | User Requirement Specification (URS) for Systems | R,A | - | - | - | - | - | - | - | D | U |  |  | -
8 | 4 | 3 | RMS Network Architecture Diagram (physical & logical) | A | R | - | - | - | - | - | - | D | U |  |  | AS
8 | 4 | 4 | Functional Specification | A | R | - | - | - | - | - | - | - | D |  |  | AS
8 | 4 | 5 | Software Design Specification | A | S | - | - | - | R | - | - | - | D |  |  | AS
8 | 4 | 6 | Hardware Design Specification | A | R | - | - | - | - | - | - | - | D |  |  | AS
8 | 4 | 7 | Operating manual | A | S | - | - | - | R | - | - | - | D |  |  | -
8 | 4 | 8 | IO list | A | S | - | - | - | R | - | - | D | U |  |  | AS
8 | 4 | 9 | Alarm list | A | S | - | - | - | R | - | - | DR | D |  |  | AS | On projects executed in COMOS list can be generated from the tool
8 | 4 | 10 | HVAC Sensor & Instrument List | A | S | - | - | - | R | - | - | D | U |  |  | AS | On projects executed in COMOS list can be generated from the tool
8 | 4 | 11 | Parameter list | A | S | - | - | - | R | - | - | - | D |  |  | AS
8 | 4 | 12 | Loop drawings HVAC | A | R | - | - | - | - | - | - | - | D |  |  | AS
8 | 4 | 13 | Pneumatic Drawings | A | R | - | - | - | - | - | - | - | D |  |  | AS
8 | 4 | 14 | FMECA Assessments all Systems (leads to Maintenance Plan & Spare Part needs) | R,A | - | - | - | - | S | - | - | - | D |  |  | -
8 | 4 | 15 | Bills of Materials | - | R | - | - | - | - | - | - | D | U |  |  | -
8 | 4 | 16 | Discipline Cost Estimates | A | R | - | - | - | - | - | D | U | U |  |  | -
8 | 4 | 17 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
8 | 5 |  | Lists, Schedules, Calculations, Reports
8 | 5 | 1 | HVAC Equipment List (Pumps, AHU, Silencer, Fan, Motor, Valves, Filter,etc) | A | R | - | - | - | - | - | DR | D | U |  |  | - | On projects executed in COMOS list can be generated from the tool
8 | 5 | 2 | HVAC Air Handling Units | A | R | - | - | - | - | - | DR | D | U |  |  | - | On projects executed in COMOS list can be generated from the tool
8 | 5 | 3 | HVAC Filter List | A | R | - | - | - | - | - | DR | D | U |  |  | - | On projects executed in COMOS list can be generated from the tool
8 | 5 | 4 | HVAC Motor Pump List | A | R | - | - | - | - | - | DR | D | U |  |  | - | On projects executed in COMOS list can be generated from the tool
8 | 5 | 5 | HVAC Actuated Valve List | A | R | - | - | - | - | - | - | D | U |  |  | - | On projects executed in COMOS list can be generated from the tool
8 | 5 | 6 | HVAC Fire Damper List | A | R | - | - | - | - | - | DR | D | U |  |  | - | On projects executed in COMOS list can be generated from the tool
8 | 5 | 7 | HVAC Air Volume Controller List | A | R | - | - | - | - | - | - | D | U |  |  | - | On projects executed in COMOS list can be generated from the tool
8 | 5 | 8 | HVAC Actuated Damper List | A | R | - | - | - | - | - | - | D | U |  |  | - | On projects executed in COMOS list can be generated from the tool
8 | 5 | 9 | HVAC Heat Exchanger List | A | R | - | - | - | - | - | DR | D | U |  |  | - | On projects executed in COMOS list can be generated from the tool
8 | 5 | 10 | HVAC Hydraulics Devices List | A | R | - | - | - | - | - | - | D | U |  |  | - | On projects executed in COMOS list can be generated from the tool
8 | 5 | 11 | HVAC Diffusor Filterbox List | A | R | - | - | - | - | - | - | D | U |  |  | - | On projects executed in COMOS list can be generated from the tool
8 | 5 | 12 | HVAC Silencer List | A | R | - | - | - | - | - | - | D | U |  |  | - | On projects executed in COMOS list can be generated from the tool
8 | 5 | 13 | HVAC Manual Damper List | A | R | - | - | - | - | - | - | D | U |  |  | - | On projects executed in COMOS list can be generated from the tool
8 | 5 | 14 | HVAC Motor Fan List | A | R | - | - | - | - | - | DR | D | U |  |  | -
8 | 5 | 15 | Utility Consumptions List | A | R | - | - | - | - | DR | D | U | U |  |  | -
8 | 5 | 16 | HVAC Cleanroom Equipment List (HEPA Boxes etc.) | A | R | - | - | - | - | - | - | D | U |  |  | -
8 | 5 | 17 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
8 | 5 | 18 | HVAC Equipment, utility and Instrument sizing calculations | A | R | - | - | - | - | - | - | D | U |  |  | -
8 | 5 | 19 | Bills of Materials | - | R | - | - | - | - | - | - | D | U |  |  | -
8 | 5 | 20 | Discipline Cost Estimates | A | R | - | - | - | - | - | D | U | U |  |  | -
8 | 5 | 21 | Design Risk Assessments | A | R | - | - | - | - | - | X,D | X,D | X,D |  |  | -
8 | 6 |  | Drawings / Schematics / Layouts / Arrangements
8 | 6 | 1 | Building Services 3D Design / Model | A | R | - | - | - | - | - | D | U | U |  |  | - | To be developed within the overall project 3D Model
8 | 6 | 2 | Pressure Flow Drawings | A | R | - | - | - | - | - | D | U | U |  |  | AS
8 | 6 | 3 | P&ID Drawings HVAC | A | R | - | - | - | - | - | - | D | U |  |  | AS
8 | 6 | 4 | HVAC Equipment Arrangement Drawings | A | R | - | - | - | - | - | DR | U | U |  |  | AS
8 | 6 | 5 | Loop drawings HVAC | A | R | - | - | - | - | - | - | - | D |  |  | AS
8 | 6 | 6 | Pneumatic Drawings | A | R | - | - | - | - | - | - | - | D |  |  | AS
8 | 6 | 7 | Mollier diagram | A | R | - | - | - | - | - | D | U | U |  |  | -
8 | 6 | 8 | Diffusor / ceiling layout | A | R | - | - | - | - | - | - | - | D |  |  | -
8 | 6 | 9 | Ducting Layouts | A | R | - | - | - | - | - | - | D | U |  |  | -
8 | 6 | 10 | Installation drawings | A | R | - | - | - | - | - | - | - | D |  |  | -
9 |  |  | PROCUREMENT
9 | 1 |  | Sourcing Strategy & Procurement Plan
9 | 1 | 1 | Sourcing Strategy | R,A | - | - | - | - | - | - | DR | D | - |  |  | -
9 | 1 | 2 | Project Procurement Plan (PPP) | A | R | S | S | S | S | - | DR | D | U | U | U | -
9 | 1 | 3 | Purchasing Documentation (project specific purchasing procedures) | R,A | S | - | - | - | - | - | D | U | U | U | U | -
9 | 1 | 4 | Project Procurement Progress Report incl. Performance KPI's, Changes/Claims | A | R | R | S | S | S | - | D | U | U | U | U | -
9 | 2 |  | Services & Trade Packages (Per Package) (No Packages = )
9 | 2 | 1 | Supplier Longlist | A | R | R | - | - | - | - | D | U | U | U | U | -
9 | 3 |  | Supplier Pre-qualification
9 | 3 | 1 | Prequalification Questionnaire (Technical, Financial, HSE and Quality) | A | R | R | - | - | - | - | - | D | D | D | D | -
9 | 3 | 2 | NVS Internal Prequalification (Vendor Quality Assessment, Performance Feedback, open Claims,..) | R,A | S | S | - | - | - | - | - | D | D | D | D | -
9 | 3 | 3 | Supplier Short List | A | R | R | - | - | - | - | - | D | U | U | U | -
9 | 4 |  | Request for Information / Budgetary Quote / Quotation)
9 | 4 | 1 | Bid Document Preparation and issuing RFQ (all commercial, technical and quality documents) | A | R | R | - | - | - | - | D | D | D | D | D | -
9 | 4 | 2 | Bid Clarification (RFI responses, Meetings, Site Visits,...) | A | R | R | - | - | - | - | X | X | X | X | X | -
9 | 4 | 3 | Technical and Commercial Bid-Analysis incl. Bid Scoring Card | A | R | R | - | - | - | - | D | D | D | D | D | -
9 | 4 | 4 | Legal Contract Comments Assessment | A | R | R | - | - | - | - | X | X | X | X | X | -
9 | 4 | 5 | Legal Negotiation | R,A | S | S | - | - | - | - | X | X | X | X | X | -
9 | 4 | 6 | Commercial Negotiation | R,A | S | S | - | - | - | - | X | X | X | X | X | -
9 | 4 | 7 | Award Recommendation | R,A | S | S | - | - | - | - | D | D | D | D | D | -
9 | 5 |  | Work Package Award
9 | 5 | 1 | Preparation of Award documentation (Insurance, Securities, Warranties, Technical, Commercial, legal,..) | R | - | - | - | - | - | - | D | D | D | D | D | -
9 | 5 | 2 | Preparation of Task Order, Work Order, SOX Documentation, Contract for Signature | R,A | S | S | - | - | - | - | D | D | D | D | D | -
9 | 5 | 3 | Letter of Intent | R,A | - | - | - | - | - |  | D | D | D | D | D | -
9 | 5 | 4 | Contract Signature | R,A | - | - | - | - | - | - | D | D | D | D | D | -
9 | 5 | 5 | Letter of Rejection | A | R | R | - | - | - | - | D | D | D | D | D | -
9 | 5 | 6 | Compilation of PO documentation | A | R | R | - | - | - | - | X | X | X | X | X | -
9 | 5 | 7 | Purchase requisition | A | R | R | - | - | - | - | X | X | X | X | X | -
9 | 5 | 8 | Update Procurement plan (Selected Supplier, Warranties, Schedule, Capex Efficiency, ...) | A | R | R | - | - | - | - | X | X | X | X | X | -
9 | 5 | 9 | Filing of Workpackage Procurement Documentation (Audit proofed) | A | R | R | - | - | - | - | X | X | X | X | X | -
9 | 6 |  | Contract Execution Management
9 | 6 | 1 | Contract Management (Adherence, Performance, Change/Claim Verification,... | A | R | R | R | - | - | - | X | X | X | X | X | -
9 | 6 | 2 | Desk Top Expediting ( including expediting of vendor documentation) | A | R | R | R | - | - | - | - | - | X | X | X | -
9 | 6 | 3 | Field Expediting & Inspections, including Reports | A | R | R | R | - | - | - | - | - | X,D | X,D | X,D | -
9 | 6 | 4 | Internal Audits (Safety, Quality, Financial, Performance,...) | R,A | S | S | S | S | S | - | X | X | X | X | X | -
9 | 6 | 5 | External Audits (Safety, Quality, Financial, Performance,...) | R,A | S | S | S | S | S | - | X | X | X | X | X | -
9 | 6 | 6 | Performance / KPI's Measurement and Corrective Actions | A | R | R | R | - | - | - | D | D | D | D | D | -
9 | 6 | 7 | Invoice (Review, Clarification, Sign Off) | A | R | R | R | - | - | - | X | X | X | X | X | -
9 | 6 | 8 | Preparation, Issue and Management of Change related PO's | A | R | R | R | - | - | - | X | X | X | X | X | -
9 | 7 |  | Closeout
9 | 7 | 1 | Final Performance and Deliverable Review (Completeness, open changes/Claims, Insurance cases,..) | R | S | S | S | S | S | - | X | X | X | X | X | -
9 | 7 | 2 | Final Invoice (Review, Clarification, Sign Off) | A | R | - | - | - | - | - | X | X | X | X | X | -
9 | 7 | 3 | Check on Securities ( Warranties, Bonds) | A | R | - | - | - | - | - | X | X | X | X | X | -
9 | 7 | 4 | Preparation and Filing of Handover documentation incl Service Level Agreements, Spare Part Management | A | R | - | - | - | - | - | X,D | X,D | X,D | X,D | X,D | -
9 | 8 |  | Equipment Packages (Per Package) (No. Packages = )
9 | 8 | 1 | Equipment Standard Verification | A | R | R | - | - | - | - | D | U | U | U | U | -
9 | 8 | 2 | Supplier Longlist | A | R | R | - | - | - | - | D | U | U | U | U | -
9 | 9 |  | Supplier Pre-qualification
9 | 9 | 1 | Prequalification Questionnaire (Technical, Financial, HSE and Quality) | A | R | R | - | - | - | - | - | D | D | D | D | -
9 | 9 | 2 | NVS Internal Prequalification (Vendor Quality Assessment, Performance Feedback, open Claims,..) | AR | S | S | - | - | - | - | - | D | D | D | D | -
9 | 9 | 3 | Supplier Short List | A | R | R | - | - | - | - | - | D | D | U | U | -
9 | 10 |  | Request for Information / Budgetary Quote / Quotation)
9 | 10 | 1 | Request for Quotation RFQ (all commercial, technical and quality documents) | A | R | R | - | - | - | - | - | D | D | D | D | -
9 | 10 | 2 | Bid Clarification (RFI responses, Meetings, Site Visits,...) | A | R | R | - | - | - | - | - | X | X | X | X | -
9 | 10 | 3 | Technical and Commercial Bid-Analysis | A | R | R | - | - | - | - | - | D | D | D | D | -
9 | 10 | 4 | Legal Contract Comments Assessment | A | R | R | - | - | - | - | - | X | X | X | X | -
9 | 10 | 5 | Legal Negotiation | AR | S | S | - | - | - | - | - | X | X | X | X | -
9 | 10 | 6 | Commercial Negotiation | AR | S | S | - | - | - | - | - | X | X | X | X | -
9 | 10 | 7 | Award Recommendation | AR | S | S | - | - | - | - | - | D | D | D | D | -
9 | 11 |  | Work Package Award
9 | 11 | 1 | Preparation of Award documentation (Insurance, Securities, Warranties, Technical, Commercial, legal,..) | R | - | - | - | - | - | - | - | D | D | D | D | -
9 | 11 | 2 | Preparation of Work Order, SOX Documentation, Contract for Signature | AR | S | S | - | - | - | - | - | D | D | D | D | -
9 | 11 | 3 | Letter of Intent | AR | - | - | - | - | - |  | - | D | D | D | D | -
9 | 11 | 4 | Contract Signature | R | - | - | - | - | - | - | - | D | D | D | D | -
9 | 11 | 5 | Letter of Rejection | A | R | S | - | - | - | - | - | D | D | D | D | -
9 | 11 | 6 | Compilation of PO documentation | A | R | R | - | - | - | - | - | X | X | X | X
9 | 11 | 7 | Purchase requisition | A | R | R | - | - | - | - | - | X | X | X | X | -
9 | 11 | 8 | Update Procurement plan (Selected Supplier, Warranties, Schedule, Capex Efficiency, ...) | A | R | R | - | - | - | - | - | X | X | X | X | -
9 | 11 | 9 | Filing of Workpackage Procurement Documentation (Audit proofed) | A | R | R | - | - | - | - | - | X | X | X | X | -
9 | 12 |  | Contract Execution Management
9 | 12 | 1 | Contract Management (Adherence, Performance, Change/Claim Verification,... | A | R | R | R | - | - | - | - | X | X | X | X | -
9 | 12 | 2 | Desk Top Expediting ( including expediting of vendor documentation) | A | R | R | R | - | - | - | - | X | X | X | X | -
9 | 12 | 3 | Field Expediting & Inspections | A | R | R | R | - | - | - | - | - | X,D | X,D | X,D | -
9 | 12 | 4 | Internal Audits (Safety, Quality, Financial, Performance,...) | A,R | S | S | S | S | S | - | - | X | X | X | X | -
9 | 12 | 5 | External Audits (Safety, Quality, Financial, Performance,...) | A,R | S | S | S | S | S | - | - | X | X | X | X | -
9 | 12 | 6 | Performance / KPI's Measurement and Corrective Actions | A | R | R | R | - | - | - | - | X | X | X | X | -
9 | 12 | 7 | Invoice (Review, Clarification, Sign Off) | A | R | R | R | - | - | - | - | X | X | X | X | -
9 | 12 | 8 | Preparation, Issue and Management of Change related PO's | A | R | R | R | - | - | - | - | X | X | X | X | -
9 | 13 |  | Closeout | [7 empty] | -
9 | 13 | 1 | Final Performance and Deliverable Review (Completeness, Closeout of Changes/Claims/Insurance cases,..) | R | S | S | S | S | S | - | - | - | X | X | X | -
9 | 13 | 2 | Final Invoice (Review, Clarification, Sign Off) | A | R | - | - | - | - | - | - | - | X | X | X | -
9 | 13 | 3 | Check on Securities ( Warranties, Bonds) | A | R | - | - | - | - | - | - | - | X | X | X | -
9 | 13 | 4 | Preparation and Filing of Handover documentation incl Service Level Agreements, Spare Part Management | A | R | - | - | - | - | - | - | - | X,D | X,D | X,D | -
10 |  |  | PRE-CONSTRUCTION
10 | 1 |  | Pre-Construction Activities during Design Phases
10 | 1 | 1 | Constructability Design Reviews & Report | - | R | - | - | - | - | - | X,D | X,D | - |  |  | -
10 | 1 | 2 | Constructability Reviews at 30, 60, 90% Model Stage | - | R | R | - | - | - | - | - | X,D | X,D | X,D |  | -
10 | 1 | 3 | Construction Compound / Facilities Layout | A | - | R | - | - | - | - | - | D | U | U |  | -
10 | 1 | 4 | Logistics and Access Plan | A | - | R | - | - | - | - | - | D | U | U |  | -
11 |  |  | COMMISSIONING & QUALIFICATION
11 | 1 |  | Commissioning & Qualification Activities during Design Phases
11 | 1 | 1 | Commissioning Master Plan | R,A | S | - | - | - | - | - | - | - | D | U |  | -
11 | 1 | 2 | Qualification Master Plan | R,A | S | - | - | - | - | - | - | - | D | U |  | -
11 | 1 | 3 | Sistem Impact Assessments (SIA) | R,A | S | - | - | - | - | - | - | D | - |  |  | -
11 | 1 | 4 | Sensor Risk Assessment (SRA) | R,A | S | - | - | - | - | - | - | - | D |  |  | -
11 | 1 | 5 | Functional Risk Assessment (FRA) | R,A | S | - | - | - | - | - | - | - | D |  |  | -
11 | 1 | 6 | Traceability Matrix | R,A | S | - | - | - | - | - | - | - | D |  | U | -
11 | 1 | 7 | Project specific SOP / Forms / Work instructions | R,A | R | - | - | - | - | - | - | D | U |  | U | -
11 | 1 | 8 | Building, Process and Utility System Lists | A | R | - | - | - | - | - | DR | D | U |  | U | -
11 | 1 | 9 | System Boundary Drawings | A | S | - | R | R | - | - | - | - | D |  | U | -
11 | 1 | 10 | FAT Test Specifications | A | R | - | R | R | - | - | - | - | X | X |  | -
11 | 1 | 11 | Perform FAT | A | R | - | R | R | - | - | - | - | - | X |  | -
11 | 1 | 12 | SAT Test Specifications | A | R | - | R | R | - | - | - | - | - | X |  | -
11 | 1 | 13 | Perform SAT | A | R | - | R | R | - | - | - | - | - | X | X | -
12 |  |  | HEALTH, SAFETY & ENVIRONMENTAL
12 | 1 |  | General Requirements
12 | 1 | 1 | HLRA High Level Risk Assessment and HSE Needs Assessment | R,A | S | - | - | - | - | - | D | U | U | U | U | -
12 | 1 | 2 | HSE Risk Management (Evaluate Legal / Local / Novartis Regs & Requirements) | R,A | S | - | - | - | - | X | - | - | - |  |  | -
12 | 1 | 3 | HSE by Design Risk Register | R,A | S | - | - | - | - | - | X | X | X | U | U | -
12 | 1 | 4 | HSE Strategy for the Project | R,A | S | - | - | - | - | - | D | U | U | U | U | -
12 | 1 | 5 | HSE System Risk Assessments | R,A | S | - | - | - | - | - |  | X | X |  |  | -
12 | 1 | 6 | HSE Design Specification | R,A | S | - | - | - | - | - |  | X | - |  |  | -
12 | 1 | 7 | HAZOP - Detailed Risk Assessment | A | R | - | - | - | - | - |  | D | U |  |  | -
12 | 1 | 8 | ZHA Process - Detailed Risk Assessment | R,A | S | - | - | - | - | - |  | X | X |  |  | -
12 | 1 | 9 | HSE Performance Reports | R,A | R | - | - | - | - | - | X | X | X | X,D | X,D | -
12 | 1 | 10 | HSE Reviews (1 to 3) | R,A | S | S | S | S | - | - | X,D | X,D | X,D |  |  | - | Reviews by Global HSE when required
12 | 1 | 11 | Construction HSE Plan | A | S | R | - | - | - | - | - | - | D | U |  | -
12 | 1 | 12 | Commissioning and Start-up HSE Plan | A | S | S | R | R | - | - | - | - | - | X | U | -
12 | 1 | 13 | HSE Incident Recording, Reporting and Investigation | - | R | - | - | - | - | - | X | X | X | X,D | X,D | -
12 | 1 | 14 | Pre-Occupation HSE Assessment | A | R | S | S | S | - | - | - | - | - | D | U | -
12 | 1 | 15 | Building Manual and Health & Safety File | A | R | S | S | S | - | - | - | - | - | D | U | -
12 | 1 | 16 | Prepare & Participate in Environment and Sustainability Assessment (HSE by Design) | R,A | S | - | - | - | - | - | D | U | U* |  |  | - | * Not Mandatory for Projects < 20MUSD
12 | 1 | 17 | Environmental Risk Assessment and Concepts | A | R | - | - | - | - | - | D | U | U |  |  | -
12 | 1 | 18 | Fire and Explosion Risk Assessments and Concepts | A | R | - | - | - | - | - | D | U | U |  |  | -
12 | 1 | 19 | Environmental and Pollution Licenses - Preparation and Submissions | R,A | R | - | - | - | - | - | - | D | U |  |  | -